# CAL Drive Strategy and Planning

Last revised September 25, 2008

Core Team: Young Yuk, Mabel Yoshimoto, Meeka Wu, Anna Phan, James Lee, Hannah Kim

### Our Intentions

We were fortunate to have huge success at the Fall 2008 CAL drive where we registered over 1,403 individuals over two days. To us, this was an unexpected and unbelievable number. We joked around that we had hoped to register 1,000 during the planning stages.  o provide some context, drives at CAL in previous years yielded 344 and 52 registrants.

We thought that if we documented what we did, it could help future college-drive coordinators use some of our ideas, in hopes of similar or better success. As a general principle, we tried to use phone or meet in-person to coordinate the logistics of this event. We found email to take longer and unnecessarily complicate matters.

### Overview

It took us a little less than 5 weeks to plan this event with Michelle as our campaign figure.  The team structure was as follows:

- Core team: 6 people, mostly alumni of the school.

- Extended team: about 5 point-persons to student organizations

- About 10 student organizations and the student government (ASUC) to help volunteer and promote the event

The marketing consisted of the following:

- A Facebook event that reached out to almost 6,000 people

- 1,500 flyers across the campus, dorms, and local businesses

- 10 classroom announcements reaching over 2,000 students

The actual drive was held on Sept 17 and 18, 2008 (Wednesday, Thursday) from 10am to 4pm.  We primarily held it at two high-traffic locations: Upper Sproul and the Campanile.  About 500 beverages were offered to those registering, which might have helped when things got busy and people had to wait (note: this required a campus permit).  At any given hour, there were roughly 25 workers on Sproul and 10 at the smaller Campanile location.  Large rally signs and t-shirts were made to draw attention and announcements were made from 12-1p at Sproul.  Fortunately, we had a record-breaking 1,403 individual registrants.

### Key Phases

Looking back, the key phases of this drive were team formation, marketing & planning, and execution.  Roughly, we marked each item in terms of how important we thought it was in terms of HIGH, MEDIUM, and LOW.

Week 1 – Team Formation

On August 15th (almost one month before the event), six of us met to talk about this drive idea that we had.  We did the following:

- HIGH - Determined the dates of the drive (about the fourth week into school)

  - We chose not to do on a Friday because lots of students do not have school.

  - Contacted AADP to confirm that these days worked for them and they committed to bringing about 6 people.

- HIGH - Generated ideas, prioritized, and assigned

  - See the Master Plan tab on our spreadsheet.  We did not execute on all of these ideas.

- MEDIUM - Developed the central theme or message

  - Our message: CAL students are known for their strength in academics and athletics, but as a school do we have heart?  Are we willing to go so far as to save lives?  Our event name was “CAL has heart.”

Week 2 – Marketing & Planning

Note: Luckily the CAL football team and Coach Tedford all registered during Fan Appreciation day where they let us hold a drive.  This was another helpful add to our marketing message.

Some of the ideas we pursued at this time were:

- HIGH - Developed our flyer.

- HIGH - Secured the locations: Upper Sproul and Campanile

  - Click here to book.  You will need two clubs to book two days.

  - The Office of Student Life in Sproul can bring out the mic for announcements between 12-1p.

- MEDIUM - Attended Calapalooza (an event where all clubs reach out to freshman) and asking every club if they would be willing to help us and forward an email to their cabinet and members.  We brought clip-boards, sign-up sheets, and flyers.

- MEDIUM - Had Michelle create a video for our mass email.

- LOW - Called local businesses to secure beverage donations (i.e. Trader Joe’s in Emeryville, Peet’s on Telegraph, and Safeway on College).

  - Each location gave us about ~100 drinks.  They need a faxed letter using AADP letterhead and their tax ID.

Week 3 – Marketing & Planning

Some of the ideas we pursued at this time were:

- HIGH - Developed the Facebook event that opened with the message “please invite everyone you know at Berkeley!”

- HIGH - Sent out requests to professors to see if we can do classroom announcements

  - We had about 10 classroom announcements that reached over 2,000 students, and it really reinforced our online efforts and brought a lot of registrants directly to our tables. In terms of planning, we figured out the top 30 classes that had the most students through schedule.berkeley.edu and got Michelle’s transcript to figure out which classes Michelle took while in college.  Then, we sent emails to these professors.  We met some resistance and some interactions took a couple of emails in order to get an exception in this life and death matter.  Click here to see the email that James sent.

- MEDIUM - Sent out our mass email to the student organizations from Calapalooza (see above) and all our friends & alumni on how they can help.

  - We asked student orgs to do three main things: 1) educate themselves; 2) invite everyone they know to our Facebook event, and; 3) sign-up to volunteer.  We probably did not need item #4 about asking for classroom announcements because the core team did those ourselves (Control-click to access the links in the email).

Week 4 – Marketing & Planning

Some of the ideas we pursued at this time were:

- HIGH - Attended general meetings of our sponsor clubs to do 3-5 speeches to enlist more volunteers.  We used Michelle’s video for the first minute.

- HIGH - Asked point-persons to try to enlist more volunteers from their student orgs.

- HIGH - Tried to make sure that we had enough tents, chairs and tables.

  - We were lucky to find a source that offered us 30 chairs and 4 tables.

  - AADP had 3 tents, 6 tables, and 15 chairs.

- HIGH - Developed double-sided rally signs and purchased materials.

- MEDIUM - Seeked approval for flyers to be posted in the dorms.

Week 4.5 – Marketing & Planning

Some of the ideas we pursued at this time were:

- HIGH - Asked point-persons to try to enlist more volunteers from their student orgs.

- HIGH - Made classroom announcements the Monday and Tuesday before the drive.

- HIGH - Sent a Facebook message to those who subscribed to the event.

- HIGH - Emailed volunteers in order to get ready for the drive.

- MEDIUM - Flyered local businesses on the Saturday prior to the drive on the South and North sides of campus.

- MEDIUM - Flyered the entire campus on the Monday and Tuesday before the drive with the help of two student orgs (i.e. DSP and Lambdas).

Day of Drives – Execution

Note: Fortunately, we already had over 100 ProjectMichelle T-shirts donated to us to give to volunteers.

- HIGH – Sent a Facebook message to everyone who subscribed to the event reporting the great success of Day 1 and our goals for Day 2.

- Set-up started at 8am for the 10am drive.

- There is a rush of individuals during the times when classes start and end.

- There were about 40 seats on Upper Sproul and 20 seats on the Campanile.

- Upper Sproul required about 4 medical reviewers because it would get held up.

- LOW - Someone had to bring coolers and ice for the drinks.  You will need a food/drink permit from the Office of Student Leadership and then pick it up from University Hall.

### Other Support

Beyond what we planned for, others rose to the occasion to help spread the word about Michelle.  For instance:

- Someone included our blurb in an Engineering Newsletter.

- Someone did class announcements in the classes where she got permission herself.

### Failed Ideas

There were some ideas that didn’t turn out the way we wanted.  In order to make this document concise, we won’t elaborate here.  Please let us know if you would like more information about our attempts:

- Getting a story in the Daily CAL, the campus newspaper

  - Talked to the University News Editor who found our story to un-newsworthy.  In our disappointment, we tried several different angles to try to break-through.  We were surprised by their response because we’ve had success with the press

- Having the Chancellor email the entire CAL community

- ASUC including our story in a system-wide email

- We secured the SuperDC, but it did not yield many registrants

- Seeking donations from Jamba Juice and Costco